## Sheet1
CMPT 275 Work Assignment Document
Group 11 - Team Invincible
Group Members: Jia Hui (Mandy) Xiao, Gary (Sheung Yau) Chung, Zavier Aguila, John Kyung Joon Ko, Ryan Kiew Ruelt Yean
Table 1: Feature Summary and Delivery Schedule
| All features listed in the proposal | Version 1 |  | Version 2 |  | Version 3 |  | Comments
|  | Original Plan | Delivered On | Original Plan | Delivered On | Original Plan | Delivered On
Functional Requirements | Register/Login Page
| F1 |  |  |  |  | X | 2017-11-16 | Ahead of schedule.
| F2 |  |  |  |  | X | 2017-11-16 | Ahead of schedule.
User Registration
| F3 |  |  |  |  | X | 2017-11-16 | Ahead of schedule.
Home Page
| F4 | X | 2017-11-05 |  |  |  |  | On schedule.
| F5 |  |  | X | 2017-11-16 |  |  | On schedule.
| F6 |  |  |  |  | X | 2017-11-22 | On schedule.
| F7 | X | 2017-11-12 |  |  |  |  | Delayed - due to such setting cannot be saved after changing.
Experience Viewer
| F8 | X | 2017-11-12 |  |  |  |  | Delayed - root cause due to failure of implementation of F7.
| F9 | X | 2017-11-02 |  |  |  |  | On schedule.
| F10 | X | 2017-11-02 |  |  |  |  | On schedule.
| F11 | X | 2017-11-02 |  |  |  |  | On schedule.
| F12 | X | 2017-11-05 |  |  |  |  | On schedule.
| F13 | X | 2017-11-02 |  |  |  |  | On schedule.
| F14 | X | 2017-11-05 |  |  |  |  | On schedule.
| F15 | X | 2017-11-06 |  |  |  |  | On schedule.
Experience Editor Start Page
| F16 |  |  | X | 2017-11-16 |  |  | On schedule.
| F17 |  |  | X | 2017-11-16 |  |  | On schedule.
| F18 |  |  |  |  | X | 2017-11-18 | On schedule.
| F19 |  |  | X | 2017-11-16 |  |  | On schedule.
| F20 |  |  | X | - |  |  | Not Implemented - due to required library exceeding the maximum file size allowed on Github.
| F21 |  |  | X | 2017-11-18 |  |  | On schedule.
| F22 |  |  | X | 2017-11-18 |  |  | On schedule.
| F23 |  |  | X | 2017-11-02 |  |  | On schedule.
| F24 |  |  |  |  | X | 2017-11-30 | On schedule.
| F25 |  |  |  |  | X | 2017-12-2 | On schedule.
| F26 |  |  |  |  | X | 2017-11-25 | On schedule. Delete button now on the start page.
| F27 |  |  |  |  | X | 2017-12-2 | On schedule.
| F28 |  |  |  |  | X | 2017-11-23 | On schedule.
Non-functional Requirements | Accessibility
| REQ1 |  |  |  |  | X | 2017-12-2 | On schedule.
| REQ2 |  |  |  |  | X | 2017-12-2 | On schedule.
Performance Requirements
| REQ3 |  |  |  |  | X | 2017-12-2 | On schedule. Can be slow due to slow Wi-Fi.
| REQ4 |  |  |  |  | X | - | Not Implemented - due to F20.
| REQ5 |  |  |  |  | X | 2017-12-2 | On schedule.
| REQ6 |  |  |  |  | X | 2017-12-2 | On schedule.
| REQ7 |  |  |  |  | X | 2017-12-2 | On schedule.
Hardware Requirements
| REQ8 | X | 2017-11-06 |  |  |  |  | App is developed for the iPad platform.
Table 2: Fulfillment of Requirements
CMPT 275 Project Requirement |  | Fulfillment of Requirement? [X] |  | Justification of fulfillment (Explain why your application fulfills this requirement)
Data Input: Mechanism of input, manual or read a dataset from a file, or from a web site (e.g. User entered data, data from other sensors, RSS feeds) |  | [ ] NO [X] YES |  | We filfulled the data input requirement by collcting information from a user in the forms of username, email, and password to register and login an account that the user has entered into correct textfields. Users are also allowed to upload panoramas, videos, and buttons to create experiences. Moreover, once an account has logged in, experiences tied to the account are loaded from the Firebase database to the app.
Archiving: Some of the information will be saved in an archive form. For example: SQL database (e.g., mySQL), flat file, or an online data storage (search the Web) |  | [ ] NO [X] YES |  | Archiving was an essential requirement to complete in our app, Prep, due to the fact that we wanted to allow account store and save experiences for later use. Moreover, we want each user to be able to create experiences tied to an account. To do this we used Firebase SDK as our database to store these assets.
Analysis: The application will in some way perform analysis function to the data collected. For example, data search (discovering specific services/products among those available), sorting, regression analysis, other statistical analysis, etc. |  | [ ] NO [X] YES |  | To fulfilled the analysis requirement, we place button in the panorama. they can then be used to trigger videos and sounds in the environment. When a user wants to place a button in a panorama to make an experience, they must touch the screen to drag the button to a location. This button is originally in 2D coordinate information, while the panoramic environment they are place is a 3D coordinate space. To transform the user's button drag from 2D to 3D coordinates, our team utilized some functions to analyze this data to convert to 3D coordinates. With the help of functions called translation and unprojectpoint the 2D data is converted to 3D coordinates so that the button is placed where it should be with depth of the button accounted for.
Display: Visualization of the analysis results (perhaps using graphs and charts.) |  | [ ] NO [X] YES |  | To display analysis results, we allow for panorama experiences with buttons, that play sound or video, that a user has placed in the panorama which they can naviagte through and play these buttons.
Network Components: The system must have components that are accessible over the Web, using a web browser or a specialized application client (e.g. Wi-Fi and cellular network connectivity) |  | [ ] NO [X] YES |  | Prep utilizes network components such as Wi-Fi and cellular network connectivity. We allow users to access stored pictures, videos, sound bites, premade experiences, and user made experiences. These assets are stored in an online cloud service, via Firebase, where we also have stored user account information. This is done so that each user has their own set of panoramic experiences they would like to use, share, or modify to their liking.
Mobile feature: Utilizing at least one feature of the particular mobile platform (in additional to Wi-Fi and cellular network connectivity), for example: accelerometer, GPS location, camera, video recording, etc. |  | [ ] NO [X] YES |  | Mobile features that have been fulfilled include the accelerometer, and video/audio recorder feature available on apple products. The accelerometer is used to navigate though the panorama in a 360 degree horizontal matter, but this can be turned off in favor of swipe navigation if preferred. Lastly, Prep implements the video recorder function, as our app allows users to take videos and sounds that can be used in the creation, with the panorama they have selected, to create an experience.